## Brief Progress
SPACE-NETWORK IMAGE TRANSFER — ABRIDGED PROGRESS REPORT
Snapshot | 2026-09-08T09:47:48+02:00
Objective | Evaluate the existing OCI/AAP2/BPv7/µD3TN image-transfer route under LEO, Lunar and Mars conditions.
Representative image | ghcr.io/siderolabs/flannel:v0.27.4
Planned matrix | 3 scenarios × 3 interruption durations × 10 repetitions
OVERALL PROGRESS | Value
Planned runs | 90
Recorded runs | 85
Progress | 94.4%
Successful | 40
Failed | 45
Pending | 5
CONDITION | RUNS | SUCCESS | FAILURE | STATUS / OBSERVATION
LEO — 10 seconds | 10 | 10 | 0 | Short outage recovered
LEO — 5 minutes | 10 | 10 | 0 | Five-minute outage recovered
LEO — 1 hour | 10 | 0 | 10 | Receiver completion timeout after long outage
LUNAR — 10 seconds | 10 | 10 | 0 | Recovered with configured 2.6 s RTT
LUNAR — 5 minutes | 10 | 10 | 0 | Recovered after reconnection
LUNAR — 1 hour | 10 | 0 | 10 | Receiver completion timeout after long outage
MARS — 10 seconds | 10 | 0 | 10 | TCPCL connection timeout before BPv7 delivery
MARS — 5 minutes | 10 | 0 | 10 | TCPCL connection timeout before BPv7 delivery
MARS — 1 hour | 5 | 0 | 5 | Still running/pending; same TCPCL limitation expected
CONFIGURED PROFILE | RTT | ONE-WAY DELAY | BANDWIDTH | SOURCE
LEO | 50 ms | 25 ms | 6 Mbit/s | Starlink measurement study; not from the IMC DSN paper
Lunar | 2.6 s | 1.3 s | 20 Mbit/s | RTT from supplied IMC DSN paper; bandwidth from NASA LLCD
Mars | 1,800 s | 900 s | 5 Mbit/s | RTT from supplied IMC DSN paper; bandwidth from JPL optical profile
KEY FINDING | 10-second and 5-minute LEO/Lunar outages recover; one-hour outages time out. Literal Mars RTT prevents TCPCL connection establishment.
IMPORTANT | A blank destination digest on failed runs means Harbor was not reached; it is not evidence of image corruption.
LIMITATIONS | One representative image; 900-run all-image scope unconfirmed. Some long runs include host sleep/WSL suspension. Mars tests characterize TCPCL, not DTN in general.
NEXT TEST | A separate one-hour scheduled-contact store-and-forward validation is queued after the baseline reaches 90 rows.
DETAILED EVIDENCE | experiments/scenarios/results/scenario_results.csv
RUN LOGS | experiments/scenarios/logs/
GRAPHS | experiments/scenarios/results/graphs/
FULL NOTE | experiments/scenarios/INTERIM_RESULTS_FOR_PROFESSOR.md